## Slide 1
Deliverables: Fully installed and configured Tire Hotel Web Application Production Environment (Azure) Knowledge transfer and solution handover Post Go-Live Extended Support
Transparency, Integrity and Accountability
Budget : US$ 87K
Initial cost : 87.3K
Running cost: 36K
1 Hosting cost : US$ 36K
2 Maintenance and Support : US$ 24K
(including penetration test)
Goal: To replace the current manual business operations using FAX and MKS system with a new Web Application.
Benefits: Eliminate manual operations using FAX on the customer side. Eliminate manual operations using MKS system on the vendor side. Catch up with other competitors that use Web Applications for Tire Hotel. Satisfy the customer of Toyota Mobility Service by providing them with a Web Application on the Goodyear side..
Scope: Implementation of Tire Hotel Web Application on Azure Only replacing CEC’s Access application Knowledge transfer Integration and user acceptance testing (UAT) Cutover standby assistance and Post Go-Live extended support
Out of Scope: No process changes in the Tire Hotel business
Project Organization:
Executive Sponsor: Yujiro Kanahara
Steering Committee: Mitsuru Nishida, Shigenobu Kato, Shig Nishida, Sree Changat, Marvin Chia, Jairo Panopio
Business Process Owner: Takayuki Hirata
IT Project Manager : Akira Tsuchiya
Team Members: Business Team: Michiyo Okada, Shinji Mizuie
IT Team : Hiroshi Yokoo, Keiichi Igarashi
Description | Cost (KUSD) | Comment
System Development | 79.4 | 
Contingency | 7.9 | Including maintenance cost 11.7K
Project Charter: Tire Hotel
Initial Cost

## Slide 2
2
Gatekeepers | Signature |  | Date
Yujiro Kanahara |  |  | 
Mitsuru Nishida |  |  | 
Shigenobu Kato |  |  | 
Shig Nishida |  |  | 
Ercan Aydemir |  |  | 
Sree Changat |  |  | 
Jairo Panopio |  |  | 
Marvin Chia |  |  | 
Sign-Off
Request approval to proceed with the following in order.
Creation of Green Budget
Creation of Shopping Cart and PO via Corporate Office
Proceed with acquisition of licenses and project execution
Project Team will consult with the Steering Committee for advise if there are any concerns with the first 2 steps.